## Slide 1: Implementation of Web Portal 1.0
Project Roadmap
Date | 20-JUN-2022
Business Contact | NARMADHA
Project Reference | PR-200622
Application | Web based admin portal
Tech Stack | PHP, MYSQL, AWS

## Slide 2
Project Goal & Vision
Scope of Work
Vendor Evaluation & Criteria
Approach / Methodology
Project Timeline
Implementation Plan
Proposed Team Structure
Cost Monitoring
Technical Stack
Conclusion
Escalation Mechanism
A G E N D A

## Slide 3
To Analyze, Develop and Implement - Web based admin Portal for Internal User admin management
Business Process Study
Setup AWS Platform
Design & Development Application
Support & Maintenance
PROJECT VISION

## Slide 4
PROJECT SCOPE
The project scope is to emphasize and enabling Web portal for User administration with salient features as below.,
    New User Registration
    User & Role management
    Customer management
    eKYC Validation Screening / Settings
    Credit and Refunds Processing
    Claims Backoffice processing
    Setting up Notifications
    Reports management
    Dashboard View management
    Export Member & Claims data

## Slide 5
VENDOR EVALUATION
Vendor assessment has been carried out using Weighted-Point method and below are the key criteria’s for evaluation
    Business (Presence / Stability / Integrity)
    Technical Competency (Capability / Delivery)
    SOW & Agreements
    Quality & Service
Detailed evaluation of multiple (sample) vendors has been carried out across different criteria’s in the attached sheet

## Slide 6
APPROACH
Business Study & Platform Setup
Setup Environment for Develop, Test and Production
Implementation of Web Application
Design the Front end and Back-end architecture
Unit, System & Pre-UAT Testing
Application packaging and deployment into Test
UAT and Sign off
Analyze the business goals and needs
Requirements Gathering & Solutioning Alignment
Define User , Role and Accessibility controls
Development of Web application using PHP and MYSQL
Application Hosting / Implementation to Production
DELIVERY MODEL
Agile Delivery Model

## Slide 7
Project Phase | Scope of Deliverables
Discovery | Process Study / Gap Analysis ; BRD Sign off
Design | High Level Design Document; Technical Architecture Tech Design Document
Development | Source Code development; Code Review Global and Local components setup / code handling Error Handling Unit Testing
Testing | Functional Test Cases / scripts ; Test case Execution Results Defect management and Test summary report
UAT | Business Test Cases / scripts; UAT Sign off
Deployment | Deployment setup Configuration management User manual Perform deployment of Code / Configurations
GO-LIVE | Prod Deployment Run book; Release specifications Deployment documents; Project Closure Sign off
ROLL OUT PLAN & DELIVERABLES
Key Pointers
This Overall Roll out Plan will be internally accommodated with Sprint wise plan as per Slide 6.
Every Sprint will undergo all the deliverables within sprint timeline of 3 weeks across design, development and testing stages

## Slide 8
PROPOSED TEAM STRUCTURE
Business
Vendor IT
Internal IT
Project Manager
XYZ1
Tech Lead
ABC1
Internal IT – Business / Vendor management
Developers
3 Developers
Change Management
XYZ2
Business Users
XYZ4
Business Analyst
XYZ3
Testing / Quality
2 Testers
Business Managers
XYZ5
Management/ Sponsor
Business Sponsor
XYZ
Project Delivery
ABC
Execution
Project Manager

## Slide 9
Expertise in Full Stack development
Experience in API Integrations , PHP and React.js
Experience in Cloud platform implementations
Expertise in web application hosting
Data analytics and dashboards
TECHNICAL STACK

## Slide 10
PROJECT COST MONITORING
NOTE – Attached Sheet contains the details of Cost Planning, tracking and Overall Project Dashboard view

## Slide 11
PROJECT STATUS SUMMARY
Internal planning and execution of plans.
Requires Business involvement.
Legend:
Project implementation.
Training and user acceptance testing (“UAT”) which requires Business involvement.
Go live.
Completed.
Work In Progress
Project Planning
Project initiation
Confirm requirements
Procurement of software (if any)
Installation & Configuration
Development
User Training
UAT
Sprint 1 – System LIVE/Production Rollout
Quality assurance
Development
User Training
UAT
Sprint 2 – System LIVE/Production rollout
Quality assurance
Development
(in progress)
User Training
UAT
Sprint 3 – System LIVE/Production rollout
Quality assurance
Test case development
Sprint 1
Sprint 2
Sprint 3
Procurement of hardware
Confirm requirements
Confirm requirements
Operational LIVE
Operational LIVE
Operational LIVE
Vendor / Internal IT
Business

## Slide 12: GOVERNANCE & STEERING CO
Delivery
Head
Technical
Lead/Team
Strategic Planning
Executive Review
Dispute Resolution
Relationship Management
Project Management
Planning & Tracking
Code management
Issue Resolution
Approvals
Code baseline and deployments
PM &
Users
Executive Sponsor
STEERING COMMITTE
WORKING COMMITTE
Monthly
Strategic Direction
Dispute Resolution
Escalation point for issues
Daily / Weekly
Performance review
Issue logging / tracking
Escalated issues
Project
Director
Steering Committee
Issue Resolution
Approvals
Financial Management
Change Control
Contract amendment
MANAGEMENT COMMITTE
Weekly
Performance review
Escalated issues
Commercial aspects
New scope of work (SOW)
Project
Manager
Project Status Reporting
From IT
Internal /Vendor
Client / Business
Stand-up Meeting
Escalation Level 1
Escalation Level 2

## Slide 13
With my expertise in Business & Digital transformation which involves System / Product implementation, Test & QA Engineering, Delivery & Portfolio management - It has always been ensured to enable the business with great success and enhanced customer satisfaction.
CONCLUSION
Thank You
Narmadha H