## Cost Sheet
Web Portal Implementation - Project Cost Tracker
S.No | Date | Item | Code | Planned | Incurred | Invoice Prending | Invoiced | Payment from Client | Paid to Vendor
Project Quote
|  | Hardware | HW
|  | Software | SW | 200000
|  | Infrastructure | INF
|  | Resources | RES | 120000
|  | Miscellaneous | MIS
| 20-Jan '22 | Invoice to Client | INV - R |  |  |  | 19110 | 19110
| 31-Jan'22 | Vendor - Consulting / Implementation | RES | [5 empty] | 8000
| 2022-01-01 | Total - This Month |  | 120000 | 0 | 0 | 19110 | 19110 | 8000
| 28-Feb'22 | Vendor - Consulting / Implementation | RES | [5 empty] | 4000
| 2022-02-01 | Total - This Month |  | 0 | 0 | 0 | 0 | 0 | 4000
|  | Total - Cummulative |  | 120000 | 0 | 0 | 19110 | 19110 | 12000
| Total |  | ToT | 320000 | 0 | 0 | 19110 | 19110 | 12000

## Project Dashboard
Projects - Consolidated Dashbaord
[17 empty] | Input fields |  |  | Met or exceeded KPI
Missed by less than 10%
|  |  |  | Project Schedule | [12 empty] | Computed fields |  |  | Missed by more than 10%
|  |  |  | 2021 |  |  | 2022
S.NO | Project Code | Project | Delivery Manager | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | SOW Revenue | Change Req Value | Total Value | SOW Gross Margin(%) | Loading Cost(%) | SOW Cost Of Revenue | Actual cost to-date | Spent to-date (%) | Work completed to-date (%) | Duration completed (%) | Payment Received | Pending Payment | Realized Value (%) | Realized Gross Margin at project completion | Action Plan for missed KPIs
1 | PR-200622 | Web Portal | Narmadha | [10 empty] | 320000 | 0 | 320000 | 30% | 5% | 213333.3333 | 12000 | 5.625% | 100% | 100% | 19110 | 0 | 5.972% | 96.06%
[14 empty] | 320000 |  | 320000 | 30% | [8 empty] | 5.972% | 96.06%